## Risk Register
RISK REGISTER
ID | Risk Name | Date Raised | Risk & Impact Description | Likelihood | Consequences | Overall | Proposed Mitigation | Owner | Target Date to Resolve | Status
1 | Internet Problems | 2021-09-20 | The main risk due to not having internet or just having slow internet is because it would slow down the production of the product. | Possible | Major | Moderate | Firstly reset router if that doesn't work then Research for many different ways to fix it. | Andrew Haupt |  | open
2 | BackUp Problems | 2021-09-20 | The main risk by not being able to backup the project would be the risk of lossing all the work produced. | Possible | Major | Low | Research many different methods. | Andrew Haupt |  | open
3 | Computer Problems | 2021-09-20 | The main risk of having computer problem would be not being able to finish the project on the deadline. | Possible | Major | Moderate | Restart computer if that doesn't work then Research for many different ways to fix it. | Andrew Haupt |  | open
4 | Saving Problems | 2021-09-20 | The main risk of having saving problems would be the risk of lossing all the work produced. | Possible | Major | Low | Research many different methods. | Andrew Haupt |  | open

## Issues Register
ISSUES REGISTER
ID | Date Raised | Project | Issue Title | Issue Description | Specific Deliverable/Milestone affected | Likelihood | Consequences | Overall Issue Rating | Proposed Resolution / Mitigating Action | Issue Owner | Target Date to Resolve | Progress Status / Commentary | Open / Closed
1
2
3

## Risk Matrix
Unitec RISK FRAMEWORK
Likelihood/Impact | Insignificant | Minor | Moderate | Major | Catastrophic
Almost Certain | Moderate | High | High | Extreme | Extreme
Likely | Moderate | Moderate | High | Extreme | Extreme
Possible | Low | Moderate | High | High | Extreme
Unlikely | Low | Low | Moderate | High | High
Rare | Low | Low | Moderate | Moderate | High

## Data (hidden)
Likelihood | Consequences
Almost Certain | Insignificant
Likely | Minor
Possible | Moderate
Unlikely | Major
Rare | Catastrophic